## v0.1
| Section name | Feature no. | Feature name | Item no. | Description | Covergroups/Property | Coverage % | Verification | Test name | Test Status | Priority | Expected results | Actual Results | BUG ID | Last Run | Blocked Reason
PAR-1 | Parameters | PAR-1.1 | DUT Parameter Defaults | PAR-1.1.1 | Verify all DUT top-level parameters are correctly initialized to default values. | — | 100% | UVM Elaboration + Monitor | — | Done | High | All top-level parameters match default spec. | Passed :) | — | — | —
PAR-2 | cfs_aligne | PAR-2.1 | FIFO_DEPTH | PAR-2.1.1 | Check FIFO depth parameter affects FIFO capacity and flags. | — | 100% | Monitor + Scoreboard | — | Done | High | FIFO handles configured depth properly. | Passed :) | — | — | —
|  | PAR-2.2 | ALGN_DATA_WIDTH | PAR-2.2.1 | Validate internal data width matches parameter. | — | 100% | Interface Monitor | — | Done | High | Data bus matches expected width. | Passed :) | — | — | —
PAR-3 | cfs_aligner_core | PAR-3.1 | ALGN_DATA_WIDTH | PAR-3.2.1 | Validate data width propagation inside aligner core. | — | 100% | Interface Monitor | — | Done | High | Data path width consistent. | Passed :) | — | — | —
|  | PAR-3.2 | FIFO_DEPTH | PAR-3.3.1 | Check FIFO depth within aligner core. | — | 100% | Monitor | — | Done | High | FIFO full/empty flags correct. | Passed :) | — | — | —
PAR-4 | cfs_ctrl | PAR-4.1 | ALGN_DATA_WIDTH | PAR-4.1.1 | Check that data width propagates to control logic. | — | 100% | Monitor | — | Done | Medium | Width consistent in ctrl path. | Passed :) | — | — | —
PAR-5 | cfs_regs | PAR-5.1 | ALGN_DATA_WIDTH | PAR-5.1.1 | Check data width propagation in regs. | — | 100% | Reg Model | — | Done | Medium | Address bus correct. | Passed :) | — | — | —
PAR-6 | cfs_rx_ctrl | PAR-6.1 | ALGN_DATA_WIDTH | PAR-6.1.1 | Check RX datapath width. | — | 100% | Monitor | — | Done | High | Data width correct. | Passed :) | — | — | —
PAR-7 | cfs_synch_fifo | PAR-7.1 | FIFO_DEPTH | PAR-7.1.1 | Check FIFO depth correctness. | — | 100% | Monitor | — | Done | High | FIFO handles configured depth properly. | Passed :) | — | — | —
PAR-8 | cfs_tx_ctrl | PAR-8.1 | ALGN_DATA_WIDTH | PAR-8.1.1 | Verify TX datapath width. | — | 100% | Monitor | — | Done | High | Width consistent. | Passed :) | — | — | —
IF-9 | Interfaces | IF-9.1 | Clock & Reset | IF-9.1.1 | Verify clk toggles and entire module synchronous to clk. | — | 100% | Directed + Smoke | — | Done | High | DUT runs only on rising edge of clk; no combinational X propagation. | Passed :) | — | — | —
|  | IF-9.1 | Clock & Reset | IF-9.1.2 | Verify reset_n (active low) initializes internal state and clears outputs. | — | 100% | Directed | — | Done | High | All outputs (md_tx_valid, md_tx_data, IRQ, etc.) are deasserted during reset and first valid cycle after release behaves correctly. | Passed :) | — | — | —
IF-10 | APB | IF-10.1 | APB Basic Signals | IF-10.1.1 | Verify APB bus signals: psel, penable, pwrite, paddr, pwdata, pready, prdata, pslverr. | apb_coverage.sv/cover_item & cover_reset | 100% | Assertions + Constrained-Random | — | In Progress | High | All APB read/write sequences complete; prdata matches register model; no spurious PSLVERR. | In Progress :¦ | — | — | —
|  | IF-10.1 | APB read/write modes | IF-10.1.2 | Cover pwrite = 0/1 for read and write behavior. | apb_coverage.sv/cover_item.direction | 0% | Directed + Constrained-Random | — | In Progress | High | Reads return correct prdata; writes update registers. | In Progress :¦ | — | — | —
|  | IF-10.1 | APB Data Patterns | IF-10.1.3 | Cover pwdata/prdata patterns: 0x0, 0xFFFFFFFF, 0xAAAAAAAA, counter, random. | apb_coverage.sv/wrap_cover_wr_data_0 apb_coverage.sv/wrap_cover_wr_data_1 | 0% | Constrained-Random + Scoreboard | — | In Progress | Medium | Data patterns transferred and mirrored in RAL model. | In Progress :¦ | — | — | —
|  | IF-10.2 | APB Address Alignment | IF-10.2.1 | Verify paddr[1:0] ignored — accesses treated as 4-byte aligned. | — | 0% | model + scoreboard | — | In Progress | High | Accesses with low bits non-zero are treated as word-aligned and map to same addresses as their aligned equivalents. | In Progress :¦ | — | — | —
|  | IF-10.3 | APB Wait States | IF-10.3.1 | Verify DUT handles delayed pready (wait states) correctly. | apb_coverage.sv/cover_item.length | 0% | Constrained-Random | — | In Progress | Medium | DUT responds correctly to variable pready delays without deadlock; transactions complete. | In Progress :¦ | — | — | —
|  | IF-10.4 | APB Error Handling | IF-10.4.1 | Verify PSLVERR asserted only on invalid accesses and proper error reporting. | apb_if.sv/unknown_value_pslverr_p | 100% | Constrained-Random + Fault Injection + Model + Scoreboard | — | In Progress | High | PSLVERR is asserted only for illegal accesses; prdata is defined; UVM catches errors. | In Progress :¦ | — | — | —
IF-11 | MD RX | IF-11.1 | RX Handshake Stability | IF-11.1.1 | Verify md_rx_valid remains high until md_rx_ready is asserted; md_rx_data, md_rx_offset, md_rx_size hold constant during handshake. | valid_high_until_ready_p | 0% | Constrained-Random + Assertions | — | In Progress | High | When md_rx_valid asserted, fields remain stable until ready true; no glitched data. | In Progress :¦ | — | — | —
| MD RX | IF-11.2 | RX Offset/Size Legality | IF-11.2.1 | Verify only legal combinations of (offset,size) are accepted per equations: ((ALGN_DATA_BYTES)+offset) % size == 0 and (size + offset) <= ALGN_DATA_BYTES. | — | 0% | Assertions + Constrained-Random (parameter sweep) | — | In Progress | High | Illegal combos are rejected or flagged (md_rx_err) and do not break alignment. | In Progress :¦ | — | — | —
| MD RX | IF-11.3 | RX Size Non-zero | IF-11.3.1 | Verify md_rx_size value 0 is illegal and flagged. | — | 0% | Assertions | — | In Progress | High | Any md_rx_size==0 causes md_rx_err or transaction rejection (simulated). | In Progress :¦ | — | — | —
| MD RX | IF-11.4 | RX Data Integrity | IF-11.4.1 | Verify md_rx_data payload is captured correctly by aligner (compare golden). | — | 0% | Constrained-Random + Scoreboard + Model | — | In Progress | High | Aligner receives exact md_rx_data when valid and ready handshake completes; scoreboard matches golden reference. | In Progress :¦ | — | — | —
| MD RX | IF-11.4 | RX fragmentation patterns | IF-11.4.2 | Cover fragmentation patterns: single-beat, multi-beat fragments, extreme fragmentation and short bursts. | — | 0% | Constrained-Random + Scoreboard | — | In Progress | High | Data captured intact; scoreboard matches golden model. | In Progress :¦ | — | — | —
| MD RX | IF-11.5 | RX Backpressure | IF-11.5.1 | Verify aligner responds correctly to backpressure (deassert md_rx_ready randomly). | — | 0% | Constrained-Random | — | In Progress | Medium | No data loss; md_rx_valid remains until md_rx_ready; system recovers after stalls. | In Progress :¦ | — | — | —
| MD RX | IF-11.6 | RX Error Signalling | IF-11.6.1 | Verify md_rx_err asserted only when both md_rx_valid and md_rx_ready are high and an error condition exists. | err_high_at_valid_and_ready_p | 0% | Constrained-Random + Fault Injection + Model + Scoreboard | — | In Progress | High | md_rx_err only high during valid+ready and only for real errors; otherwise low. | In Progress :¦ | — | — | —
| MD RX | IF-11.7 | Illegal offset/size classes | IF-11.7.1 | Enumerate illegal (offset,size) classes across ALGN_BYTES; verify md_rx_err or reject path for each illegal class. | — | 0% | Directed Fault Injection | — | In Progress | High | All illegal classes cause expected error signal/behavior. | In Progress :¦ | — | — | —
IF-12 | MD TX | IF-12.1 | TX Handshake Stability | IF-12.1.1 | Verify md_tx_valid remains high until md_tx_ready becomes high; md_tx_data/offset/size remain constant during handshake. | valid_high_until_ready_p | 0% | Constrained-Random + Assertions | — | In Progress | High | md_tx_valid holds until ready; outputs stable; no glitches. | In Progress :¦ | — | — | —
| MD TX | IF-12.2 | TX Offset/Size Legality | IF-12.2.1 | Verify TX only issues legal (offset,size) combos per the same equations as RX; size!=0. | — | 0% | Directed + Constrained-Random | — | In Progress | High | Aligner never transmits illegal combinations; if requested, error path exercised. | In Progress :¦ | — | — | —
| MD TX | IF-12.3 | TX Data Alignment | IF-12.3.1 | Verify that md_tx_data is correctly aligned according to offset/size and matches what aligner should produce from received unaligned stream. | — | 0% | Scoreboard (golden aligner model) | — | In Progress | High | Aligned data equals golden model for all valid cases. | In Progress :¦ | — | — | —
| MD TX | IF-12.4 | TX Error Propagation | IF-12.4.1 | Verify md_tx_err input is honored: when md_tx_err is asserted (during valid+ready), aligner handles error. | — | 0% | Fault Injection | — | In Progress | High | Error is propagated into status registers/IRQ; no data corruption beyond error. | In Progress :¦ | — | — | —
| MD TX | IF-12.5 | TX Backpressure & Flow | IF-12.5.1 | Verify aligner backpressure handling when downstream deasserts md_tx_ready for extended cycles (no underflow/overflow). | — | 0% | Constrained-Random + Random Stall | — | In Progress | Medium | No FIFO underflow/overflow; valid holds until ready asserts as required. | In Progress :¦ | — | — | —
|  | IF-12.6 | TX size==0 cases | IF-12.6.1 | Explicitly test md_tx_size==0 is rejected/flagged. | — | 0% | Directed | — | In Progress | High | size==0 never allowed; error signalled. | In Progress :¦ | — | — | —
IF-13 | Cross-IF | IF-13.1 | RX→TX Consistency | IF-13.1.1 | End-to-end test: receive unaligned stream on RX and verify aligned stream on TX for many sizes/offsets. | — | 0% | Constrained-Random + Model | — | In Progress | High | For all valid input sequences, TX output sequence equals golden aligned reference; coverage close to 95–100%. | In Progress :¦ | — | — | —
|  | IF-13.2 | Simultaneous Transactions | IF-13.2.1 | Verify module handles concurrent APB activity and MD traffic (i.e., register reads/writes while RX/TX active). | — | 0% | Virtual Sequences + Model + Scoreboard | — | In Progress | Medium | No deadlocks or unexpected behavior; APB ops succeed while MD streams active. | In Progress :¦ | — | — | —
| IRQ | IF-13.3 | Interrupt Behavior | IF-13.3.1 | Verify irq asserts on interrupt conditions. | — | 0% | Constrained-Random + Reg Model + Model | — | In Progress | High | irq asserted on correct conditions; status registers reflect source; interrupt cleared properly. | In Progress :¦ | — | — | —
| Observability | IF-13.4 | Signal Stability | IF-13.4.1 | Verify that signals that must remain constant during valid (data/offset/size) do not glitch during handshake and at clock boundaries. | — | 0% | Assertions | — | In Progress | High | No mid-handshake changes; waveform holds stable through handshake. | In Progress :¦ | — | — | —
IF-14 | Timing | IF-14.1 | Reset timing scenarios | IF-14.1.1 | Reset asserted during idle, during active transfer, and just-before-ready; verify safe behavior and correct abort/complete behavior. | — | 0% | Directed + Assertions | — | In Progress | High | Reset clears outputs; no data corruption; transfers abort/complete per spec. | In Progress :¦ | — | — | —
|  | IF-14.1 | Clock edge / metastability stress | IF-14.1.2 | Drive md_* signals close to clock edges, jitter tests, and check for metastability/hold violations. | — | 0% | Timing Stress + Assertions | — | In Progress | High | No undetected metastability; timing assertions pass or documented. | In Progress :¦ | — | — | —
REG-15 | Registers | REG-15.1 | Register map decoding | REG-15.1.1 | Cover all valid register addresses (CTRL, STATUS, IRQEN, IRQ). | — | 0% | Directed + RAL Model | — | In Progress | High | Reads/writes succeed on valid addresses only. | In Progress :¦ | — | — | —
|  |  |  | REG-15.1.2 | Access unmapped addresses; expect APB error. | — | 0% | Directed | — | In Progress | High | Unmapped access triggers PSLVERR; no side effects. | In Progress :¦ | — | — | —
|  | REG-15.2 | Register access types | REG-15.2.1 | Cover read/write/RO/WO/W1C accesses per register field. | — | 0% | RAL Sequence + Directed | — | In Progress | High | RO ignores writes; WO reads return 0; W1C clears only on 1. | In Progress :¦ | — | — | —
|  |  |  | REG-15.2.2 | Attempt write to full RO register (STATUS); expect APB error. | — | 0% | Directed | — | In Progress | High | Write to RO register asserts PSLVERR; no value changed. | In Progress :¦ | — | — | —
|  |  |  | REG-15.2.3 | Attempt read from full WO register (if applicable); expect APB error. | — | 0% | Directed | — | In Progress | High | Read from WO returns PSLVERR; value 0. | In Progress :¦ | — | — | —
|  | REG-15.3 | Control Register (CTRL) | REG-15.3.1 | Cover all fields SIZE, OFFSET, CLR. | — | 0% | Directed + RAL Access | — | In Progress | High | SIZE/OFFSET/CLR written and read per access type. | In Progress :¦ | — | — | —
|  |  |  | REG-15.3.2 | Write SIZE=0 → APB error. | — | 0% | Directed | — | In Progress | High | PSLVERR asserted, SIZE not updated. | In Progress :¦ | — | — | —
|  |  |  | REG-15.3.3 | Write illegal (SIZE,OFFSET) combination → APB error. | — | 0% | Directed Sweep | — | In Progress | High | PSLVERR asserted for illegal SIZE/OFFSET combos. | In Progress :¦ | — | — | —
|  |  |  | REG-15.3.4 | Write valid (SIZE,OFFSET) combinations; verify proper storage. | — | 0% | Constrained-Random + RAL | — | In Progress | High | Values update; no error flagged. | In Progress :¦ | — | — | —
|  |  |  | REG-15.3.5 | CLR bit behavior (WO): write 1 clears CNT_DROP; read always returns 0. | — | 0% | Directed | — | In Progress | Medium | CNT_DROP resets after write 1; read value=0. | In Progress :¦ | — | — | —
|  | REG-15.4 | Status Register (STATUS) | REG-15.3.1 | Cover read-only behavior; verify TX_LVL, RX_LVL, CNT_DROP readable only. | — | 0% | Directed + RAL Mirror | — | In Progress | High | RO fields readable; write ignored; values match DUT. | In Progress :¦ | — | — | —
|  |  |  | REG-15.3.2 | Check CNT_DROP increments on unaligned access; saturates at max. | — | 0% | Directed + End-to-End | — | In Progress | High | CNT_DROP increments, saturates, no wrap. | In Progress :¦ | — | — | —
|  |  |  | REG-15.3.3 | Read STATUS while activity ongoing; verify no read corruption. | — | 0% | Directed | — | In Progress | Medium | Consistent reads during streaming; no glitch. | In Progress :¦ | — | — | —
|  | REG-15.5 | IRQ Enable Register (IRQEN) | REG-15.5.1 | Cover RW access to IRQEN bits (RX_EMPTY, RX_FULL, TX_EMPTY, TX_FULL, MAX_DROP). | — | 0% | Directed + RAL | — | In Progress | High | Bits RW; writes take effect; reads match writes. | In Progress :¦ | — | — | —
|  |  |  | REG-15.5.2 | Verify reserved bits (RO) always 0 and not writable. | — | 0% | Directed | — | In Progress | Medium | Reserved bits ignore writes; always 0. | In Progress :¦ | — | — | —
|  | REG-15.6 | IRQ Register (IRQ) | REG-15.6.1 | Cover all W1C bits (RX_EMPTY, RX_FULL, TX_EMPTY, TX_FULL, MAX_DROP). | — | 0% | Directed + Event Injection | — | In Progress | High | Writing 1 clears bit; 0 leaves it unchanged. | In Progress :¦ | — | — | —
|  |  |  | REG-15.6.2 | Clear IRQ while condition still active; verify sticky reassertion later. | — | 0% | Directed | — | In Progress | High | Bit clears then reasserts when condition persists. | In Progress :¦ | — | — | —
|  |  |  | REG-15.6.3 | Verify RO reserved bits always 0. | — | 0% | Directed | — | In Progress | Low | Reserved bits constant 0. | In Progress :¦ | — | — | —
|  | REG-15.7 | APB error scenarios | REG-15.7.1 | Write illegal SIZE=0, illegal OFFSET/SIZE combo → PSLVERR. | — | 0% | Directed | — | In Progress | High | PSLVERR asserted; registers not updated. | In Progress :¦ | — | — | —
|  |  |  | REG-15.7.2 | Write to RO register (STATUS) → PSLVERR. | — | 0% | Directed | — | In Progress | High | PSLVERR asserted; no value changed. | In Progress :¦ | — | — | —
|  |  |  | REG-15.7.3 | Read from WO register (if any) → PSLVERR. | — | 0% | Directed | — | In Progress | Medium | PSLVERR asserted; no valid data returned. | In Progress :¦ | — | — | —
|  |  |  | REG-15.7.4 | Access unmapped address → PSLVERR. | — | 0% | Directed | — | In Progress | High | PSLVERR asserted; no side effect. | In Progress :¦ | — | — | —
|  | REG-15.8 | Reset behavior | REG-15.8.1 | Verify all registers reset to default values per spec. | — | 0% | Directed + RAL Reset Test | — | In Progress | High | After reset, all registers equal reset value. | In Progress :¦ | — | — | —
|  |  |  | REG-15.8.2 | Verify no latch-up or illegal values after multiple resets. | — | 0% | Directed | — | In Progress | Medium | Multiple resets restore all fields to reset value. | In Progress :¦ | — | — | —
FUNC-16 | Functionality | FUNC-16.1 | Basic Alignment Mapping | FUNC-16.1.1 | Verify alignment mapping behavior for CTRL.SIZE=1, CTRL.OFFSET=0 with ALGN_DATA_WIDTH=32 (single-byte aligned outputs as in Figure 6). | — | 0% | Directed (vector) + Scoreboard | — | In Progress | High | For provided RX stream, TX bytes are produced in expected order per figure; scoreboard matches golden. | In Progress :¦ | — | — | —
|  |  |  | FUNC-16.1.2 | Verify alignment for CTRL.SIZE=1, CTRL.OFFSET=2 (Figure 7 pattern). | — | 0% | Directed + Scoreboard | — | In Progress | High | TX mapping follows figure; no lost/duplicated bytes. | In Progress :¦ | — | — | —
|  |  |  | FUNC-16.1.3 | Verify alignment for CTRL.SIZE=2, CTRL.OFFSET=2 (Figure 8). | — | 0% | Directed + Scoreboard | — | In Progress | High | Two-byte grouping correct; TX groups reflect expected concatenation. | In Progress :¦ | — | — | —
|  |  |  | FUNC-16.1.4 | Verify alignment for CTRL.SIZE=4, CTRL.OFFSET=0 (Figure 9). | — | 0% | Directed + Scoreboard | — | In Progress | High | Four-byte aligned outputs produced; golden matched. | In Progress :¦ | — | — | —
FUNC-17 | Functionality | FUNC-17.1 | Full sweep of (SIZE,OFFSET) legal combos | FUNC-17.1.1 | Sweep all legal (SIZE,OFFSET) pairs for ALGN_DATA_BYTES=4 (ALGN_DATA_WIDTH=32) and check mapping correctness for several RX patterns. | — | 0% | Constrained-Random Sweep + Scoreboard | — | In Progress | High | All legal pairs produce TX sequences identical to golden model. | In Progress :¦ | — | — | —
|  | FUNC-17.2 | Illegal (SIZE,OFFSET) detection | FUNC-17.2.1 | Inject illegal (SIZE,OFFSET) combos on CTRL write or via illegal RX descriptors; expect APB error on illegal CTRL write and md_rx_err on illegal RX. | — | 0% | Directed Fault Injection | — | In Progress | High | Illegal CTRL writes → PSLVERR; illegal RX combos → md_rx_err asserted and sequence rejected/flagged. | In Progress :¦ | — | — | —
FUNC-18 | Behavior | FUNC-18.1 | Handshake invariants during alignment | FUNC-18.1.1 | Verify valid/ready semantics: md_rx_valid holds until md_rx_ready; md_tx_valid holds until md_tx_ready; and data/offset/size stable during handshake. | — | 0% | Assertions + Constrained-Random | — | In Progress | High | No mid-handshake changes; assertions pass. | In Progress :¦ | — | — | —
|  | FUNC-18.2 | Timing / boundary cases | FUNC-18.2.1 | Drive md_rx_valid assertions at and near clock edges (setup/hold stress) to surface metastability/hold violations during alignment. | — | 0% | Timing Stress + Assertions | — | In Progress | High | No data corruption; any timing violations reported; alignment still correct or fail documented. | In Progress :¦ | — | — | —
FUNC-19 | Data patterns | FUNC-19.1 | Data pattern correctness | FUNC-19.1.1 | Use representative data patterns (0x00.., 0xFF.., 0x11223344, alternating, counters) to ensure aligner copies payload bits correctly across byte/word boundaries. | — | 0% | Constrained-Random + Scoreboard | — | In Progress | Medium | For each pattern, TX equals golden aligned output. | In Progress :¦ | — | — | —
|  | FUNC-19.2 | Fragmentation extremes | FUNC-19.1.2 | Exercise extreme fragmentation: many single-byte fragments and multi-beat fragments; verify TX assembly. | — | 0% | Stress End-to-End + Scoreboard | — | In Progress | High | Aligner merges fragments correctly into aligned TX outputs without loss. | In Progress :¦ | — | — | —
FUNC-20 | RX→TX | FUNC-20.1 | End-to-end waveform scenario (Figure 10) | FUNC-20.1.1 | Recreate waveform from Figure 10: md_rx_valid, md_rx_data=0x44332211, offset=2, size=3 (example), observe md_tx timing/values as shown. | — | 0% | Directed Waveform Replay + Scoreboard | — | In Progress | High | TX waveform matches figure timing and values; offsets/sizes per-beat correct. | In Progress :¦ | — | — | —
FUNC-21 | Control interactions | FUNC-21.1 | CTRL write while streaming not allowed | FUNC-21.1.1 | Attempt illegal write to CTRL.SIZE or CTRL.OFFSET while MD stream active if spec forbids — expect APB error or specified behavior. | — | 0% | Directed + APB Sequences | — | In Progress | High | Either PSLVERR or defined behavior per spec; no corruption. | In Progress :¦ | — | — | —
|  | FUNC-21.2 | Valid CTRL updates between transactions | FUNC-21.2.1 | Update CTRL.SIZE/OFFSET only between completed transactions; verify next RX→TX uses new config. | — | 0% | Directed Sequence + End-to-End | — | In Progress | High | New SIZE/OFFSET applied only after current transaction completes; TX uses new settings subsequently. | In Progress :¦ | — | — | —
FUNC-22 | Error handling | FUNC-22.1 | md_rx_err → effect on TX & IRQ | FUNC-22.1.1 | Inject md_rx_err during valid+ready; verify that error path triggers IRQ and that partial frames are discarded or handled per spec. | — | 0% | Fault Injection + Reg Check | — | In Progress | High | md_rx_err reflected in IRQ/IRQ register and in status registers; TX does not emit corrupted data. | In Progress :¦ | — | — | —
FUNC-23 | Coverage & cross-checks | FUNC-23.1 | Cross coverage: offset×size×fragmentation | FUNC-23.1.1 | Cross-cover offset×size×fragmentation pattern to find uncovered combos that may break alignment. | — | 0% | Constrained-Random + Coverage Closure | — | In Progress | High | Coverage closure shows all relevant combos exercised; no uncovered critical combos. | In Progress :¦ | — | — | —
FUNC-24 | Performance & stress | FUNC-24.1 | Throughput & backpressure mixing | FUNC-24.1.1 | Drive continuous high-rate RX stream with intermittent downstream md_tx_ready deasserts; verify no FIFO overflow/underflow and alignment correctness. | — | 0% | Long-run Stress Regression | — | In Progress | Medium | No data loss; counters and STATUS reflect levels; alignment preserved. | In Progress :¦ | — | — | —
FUNC-25 | Regression & monotonic checks | FUNC-25.1 | Regression regressionization (repeatability) | FUNC-25.1.1 | Repeat key alignment tests with different seeds and builds to ensure deterministic failure reproduction and stability across releases. | — | 0% | Regression CI + UCDB | — | In Progress | Medium | Tests reproducible; UCDB shows consistent coverage across runs. | In Progress :¦ | — | — | —
FC-26 | Flow Control | FC-26.1 | RX Controller - Backpressure | FC-26.1.1 | md_rx_ready asserted when RX FIFO has space; deasserted when RX FIFO full. | — | 0% | Directed + Constrained-Random | — | In Progress | High | md_rx_ready == 1 when RX_LVL < FIFO_DEPTH; md_rx_ready == 0 when RX_LVL == FIFO_DEPTH. | In Progress :¦ | — | — | —
|  | FC-26.2 | RX Controller - Full/Empty thresholds | FC-26.2.1 | Verify RX FIFO boundary transitions (N-1 → N full, 1 → 0 empty) reflected in STATUS.RX_LVL and IRQ sticky bits. | — | 0% | Directed + Event Injection | — | In Progress | High | STATUS.RX_LVL increments/decrements correctly; IRQ.RX_FIFO_FULL set on full transition, IRQ.RX_FIFO_EMPTY set on empty transition and sticky until cleared. | In Progress :¦ | — | — | —
|  | FC-26.3 | RX Controller - Illegal MD detection | FC-26.3.1 | Verify legality equations for incoming transfer; illegal → md_rx_err and CNT_DROP++ (saturates). | — | 0% | Directed Sweep + Scoreboard | — | In Progress | High | Illegal (offset,size) → md_rx_err asserted during valid+ready; STATUS.CNT_DROP increments until MAX then saturates. | In Progress :¦ | — | — | —
|  | FC-26.4 | CNT_DROP saturation & CLR behavior | FC-26.4.1 | When CNT_DROP reaches max, remains at max; writing CTRL.CLR=1 resets to 0; IRQ.MAX_DROP sticky behaviour. | — | 0% | End-to-End + APB reg write | — | In Progress | High | CNT_DROP stops incrementing at MAX; IRQ.MAX_DROP set when max reached; writing CTRL.CLR=1 resets CNT_DROP to 0; clearing IRQ.MAX_DROP via IRQ W1C clears sticky bit. | In Progress :¦ | — | — | —
FC-27 | Flow Control | FC-27.1 | RX FIFO - Fill/Drain behavior | FC-27.1.1 | RX FIFO fill/empty under different RX traffic (steady, bursts, fragmentation). STATUS.RX_LVL reflects real level. | — | 0% | Stress + Scoreboard | — | In Progress | High | RX FIFO fill/drain levels track expected values; STATUS.RX_LVL matches instrumented FIFO level in all scenarios. | In Progress :¦ | — | — | —
|  | FC-27.2 | RX FIFO - Sticky IRQ on empty/full | FC-27.2.1 | IRQ.RX_FIFO_EMPTY/FULL sticky behavior and W1C clear semantics when condition persists. | — | 0% | Fault Injection + APB clear tests | — | In Progress | High | IRQ bit set on event and remains set until IRQ register W1C clears it; if condition persists it reasserts only after condition cycles (per spec). | In Progress :¦ | — | — | —
FC-28 | Flow Control | FC-28.1 | Controller - Read from RX FIFO and align | FC-28.1.1 | Controller reads RX FIFO when data available, aligns according to CTRL.SIZE/OFFSET and pushes to TX FIFO. | — | 0% | End-to-End + Scoreboard | — | In Progress | High | For available RX data, controller reads, aligns correctly and enqueues TX FIFO entries matching golden aligner model. | In Progress :¦ | — | — | —
|  | FC-28.2 | Controller - Wait on TX FIFO full | FC-28.2.1 | Controller halts when TX FIFO full, resumes when space is available. | — | 0% | Directed + Backpressure | — | In Progress | High | When TX FIFO full, controller stops issuing TX pushes; resumes once TX FIFO has space; no data lost or re-ordered. | In Progress :¦ | — | — | —
FC-29 | Flow Control | FC-29.1 | TX FIFO - Fill/Drain and STATUS.TX_LVL | FC-29.1.1 | TX FIFO updates STATUS.TX_LVL on enq/deq; sticky IRQ on full/empty like RX. | — | 0% | Stress + Scoreboard | — | In Progress | High | STATUS.TX_LVL accurately mirrors TX FIFO level; IRQ.TX_FIFO_FULL/TX_FIFO_EMPTY sticky and W1C semantics hold. | In Progress :¦ | — | — | —
|  | FC-29.2 | TX FIFO - Underflow/Overflow protection | FC-29.2.1 | Underflow never occurs when md_tx_valid/ready handshake respected; overflow avoided by controller backpressure. | — | 0% | Fault Injection + Long-run Stress | — | In Progress | High | No underflow/overflow observed; controller/tx_ready handshake prevents corruption. | In Progress :¦ | — | — | —
FC-30 | Flow Control | FC-30.1 | TX Controller - md_tx handshake | FC-30.1.1 | TX Controller issues md_tx_valid and waits for md_tx_ready; data stable until ready asserted. | — | 0% | Constrained-Random + Assertions | — | In Progress | High | md_tx_valid holds until md_tx_ready == 1; md_tx_data/offset/size stable during handshake. | In Progress :¦ | — | — | —
|  | FC-30.2 | TX Controller - md_tx_err handling | FC-30.2.1 | When external md_tx_err asserted during valid+ready, TX Controller handles per spec (drop, report IRQ, preserve FIFO consistency). | — | 0% | Fault Injection + Reg Check | — | In Progress | High | md_tx_err results in appropriate IRQ bit set, STATUS updated, no output data corruption beyond spec. | In Progress :¦ | — | — | —
FC-31 | Flow Control | FC-31.1 | RX→TX throughput under backpressure | FC-31.1.1 | Drive high-rate RX with intermittent TX backpressure; verify sustained throughput, no data loss, FIFO usage within limits. | — | 0% | Long-run Stress | — | In Progress | Medium | System handles backpressure: md_rx_ready toggles accordingly; no dropped or corrupted frames; STATUS counters reflect behavior. | In Progress :¦ | — | — | —
FC-32 | Flow Control | FC-31.2 | STATUS register reflectivity | FC-32.2.1 | STATUS fields (RX_LVL, TX_LVL, CNT_DROP) reflect internal state and update synchronously per events. | — | 0% | Directed + Scoreboard | — | In Progress | High | STATUS register reads match internal instrumented values within one cycle or as defined by spec. | In Progress :¦ | — | — | —
|  | FC-31.3 | CNT_DROP increment semantics | FC-32.3.1 | CNT_DROP increments only on illegal MD transfers, saturates at MAX, writing CTRL.CLR clears to zero. | — | 0% | Directed Sweep + APB Write | — | In Progress | High | CNT_DROP increments on illegal cases only; saturates at MAX; CTRL.CLR resets to 0 when written 1. | In Progress :¦ | — | — | —
FC-33 | Registers / APB | FC-33.1 | APB wait-state limit | FC-33.1.1 | Verify APB transfers may introduce wait-states but never exceed 5 cycles (illegal >5 → spec violation). | — | 0% | Directed (pready delays) | — | In Progress | High | Any transfer with pready delayed >5 cycles flagged (simulator assertion) or treated per spec; report as failure. | In Progress :¦ | — | — | —
|  | FC-33.2 | APB alignment behavior | FC-33.2.1 | paddr[1:0] ignored; address treated as word-aligned. Test reads/writes with non-zero low bits map to base address. | — | 0% | Directed + Reg Model | — | In Progress | High | paddr low bits ignored; accesses mapped as word-aligned; no unexpected side effects. | In Progress :¦ | — | — | —
FC-34 | Interrupts | FC-34.1 | IRQ generation pulse semantics | FC-34.1.1 | Each interrupt event generates a 1-cycle pulse on irq regardless of enable; IRQEN controls whether event contributes to irq OR output. | — | 0% | Directed + Event Injection | — | In Progress | High | Event sets IRQ register bit; irq pulses 1 cycle when event occurs; if corresponding IRQEN bit==1 the pulse contributes to irq output. | In Progress :¦ | — | — | —
|  | FC-34.2 | IRQ sticky & W1C clearing semantics | FC-34.2.1 | IRQ register bits are sticky (W1C): write 1 clears; if condition persists the bit will set again when event reoccurs. | — | 0% | Directed + APB Clear Sequence | — | In Progress | High | Bits cleared by writing 1; if source condition persists, bit eventually reasserts per spec; IRQ output pulses accordingly. | In Progress :¦ | — | — | —
FC-35 | System | FC-35.1 | APB access during streaming | FC-35.1.1 | Interleave APB reads/writes (including CTRL writes) while RX/TX are active and verify no deadlocks and defined behavior on illegal CTRL writes. | — | 0% | Randomized Mixed Activity | — | In Progress | High | APB ops succeed when legal; illegal CTRL writes during active transfers either return PSLVERR or follow specified rule; streaming continues per spec. | In Progress :¦ | — | — | —
FC-36 | Observability | FC-36.1 | Monitor assertions & invariants | FC-36.1.1 | Add assertions: md_* stability during valid, size!=0, handshake invariants, FIFO level bounds. Cover assertion firing cases. | — | 0% | Assertions + Regression | — | In Progress | High | All assertions pass in golden runs; when violated, generate trace and UCDB entry. | In Progress :¦ | — | — | —
FC-37 | Stress / Reliability | FC-37.1 | Long-run stability & corner cases | FC-37.1.1 | Run long regressions with random legal & illegal inputs, APB ops, backpressure; verify no memory leaks, no counter wrap, correct sticky behavior. | — | 0% | Long-run Regression CI | — | In Progress | Medium | No crashes; no unexpected counter wrapping; coverage targets met; sticky flags behave per spec. | In Progress :¦ | — | — | —